## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-01 | As a user (student/faculty), I want secure JWT authentication and role-based access control so that my workspace is protected. | MUST HAVE | No Dependency | Karthik | 3- Completed
S1 | S1 | US-02 | As a student, I want an interactive onboarding wizard to input project idea details, domain, and 1-5 skill ratings so that AI gets complete context. | MUST HAVE | US-01 | Govardhan | 3- Completed
S1 | S1 | US-03 | As a developer, I want MongoDB Atlas cloud cluster initialization, connection pooling, and normalized schemas so that data is persistently structured. | MUST HAVE | No Dependency | Hemapriya | 3- Completed
S1 | S1 | US-04 | As a student, I want an autonomous Feasibility Agent (Agent 1) to evaluate technical viability, timeline viability, and skill match with 0-100 score. | MUST HAVE | US-02, US-03 | Govardhan | 3- Completed
S1 | S1 | US-05 | As a faculty guide, I want a dedicated dashboard shell and cohort schema layout so that student progress and projects can be monitored. | MUST HAVE | US-01, US-03 | Supriya | 3- Completed
S2 | S2 | US-06 | As a student and mentor, I want a Scope Definition Agent (Agent 2) to delineate In-Scope vs Out-of-Scope boundaries and deliverables to prevent scope creep. | MUST HAVE | US-04 | Govardhan | 3- Completed
S2 | S2 | US-07 | As a developer, I want sequential AI agent pipeline orchestration with LiteLLM retry backoff to handle Groq API rate limits and token spikes. | MUST HAVE | US-01, US-04 | Karthik | 3- Completed
S2 | S2 | US-08 | As a student, I want an Adaptive Tech Stack Recommender Agent (Agent 3) to suggest tailored frameworks based on team skill ratings with learning curves. | MUST HAVE | US-06 | Supriya | 3- Completed
S2 | S2 | US-09 | As a faculty guide and student, I want a Multi-Vector Risk Assessment Agent (Agent 4) and 5x5 Risk Heatmap to evaluate Probability and Impact with mitigations. | MUST HAVE | US-06, US-08 | Supriya | 3- Completed
S2 | S2 | US-10 | As a developer, I want MongoDB document persistence and local JSON storage fallback for all agent-generated analysis reports to ensure zero data loss. | MUST HAVE | US-03, US-07 | Hemapriya | 3- Completed
S3 | S3 | US-11 | As a student, I want a 5-Phase Milestone & Timeline Generator Agent (Agent 5) to create structured sprint roadmaps with estimated effort and dates. | MUST HAVE | US-06, US-08 | Karthik | 3- Completed
S3 | S3 | US-12 | As a student, I want an interactive Roadmap Timeline UI with phase accordions, task completion check-offs, and real-time progress percentage bar. | MUST HAVE | US-11 | Govardhan | 3- Completed
S3 | S3 | US-13 | As a student and mentor, I want a Dynamic Re-Planner Agent to detect milestone deadline breaches and automatically recalculate downstream schedules. | MUST HAVE | US-11, US-12 | Supriya | 3- Completed
S3 | S3 | US-14 | As a student, I want an interactive AI Mentor Chatbot with Web Speech API voice input and full project context memory to ask technical guidance questions. | SHOULD HAVE | US-07, US-10 | Govardhan | 3- Completed
S3 | S3 | US-15 | As a developer, I want MongoDB chat history indexing and conversation session persistence with query optimization under 50ms. | MUST HAVE | US-03, US-14 | Hemapriya | 3- Completed
S4 | S4 | US-16 | As a faculty guide, I want cohort analytics, at-risk student flagging, milestone sign-offs, and broadcast announcements engine. | MUST HAVE | US-05, US-12 | Supriya | 3- Completed
S4 | S4 | US-17 | As a student, I want an Academic Document Generator Agent (Agent 7) to draft formal Project Synopsis and Methodology reports ready for export. | SHOULD HAVE | US-06, US-11 | Hemapriya | 3- Completed
S4 | S4 | US-18 | As a DevOps engineer, I want Docker multi-stage containerization, CORS security, and cloud deployment pipelines (Vercel SPA + Render Backend). | MUST HAVE | US-01, US-07 | Karthik | 3- Completed
S4 | S4 | US-19 | As a QA lead, I want comprehensive end-to-end regression testing with 118 passing automated tests across all agents, routers, and workflows. | MUST HAVE | All Upstream | Karthik | 3- Completed
S4 | S4 | US-20 | As a team, I want complete Requirements Traceability Matrix (RTM), Defect Tracker, Unit Test Plan, and presentation materials for Viva defense. | MUST HAVE | All Upstream | Hemapriya | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours ¦ 4 Sprints × 14 Calendar Days (10 Working Days)
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
TOTAL REMAINING EFFORT:
SPRINT 1 BACKLOG — Foundation, Auth, Mongo Atlas & Feasibility Engine
US-01 | TS-101 | Implement FastAPI JWT token authentication and bcrypt password hashing | 2024-11-04 | 2024-11-06 | Karthik | Coding | 3- Completed | 8 | 8 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | TS-102 | Build /auth/login and /auth/register endpoints with Pydantic validation | 2024-11-06 | 2024-11-08 | Karthik | Coding | 3- Completed | 6 | 6 | 6 | 6 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | TS-103 | Write pytest test suite for auth routes and token expiration verification | 2024-11-09 | 2024-11-11 | Karthik | Unit Test | 3- Completed | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | TS-104 | FastAPI core application setup, CORS middleware, and error handlers | 2024-11-04 | 2024-11-05 | Karthik | Build | 3- Completed | 4 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | TS-105 | Design React 19 Onboarding multi-step wizard and domain selection UI | 2024-11-04 | 2024-11-06 | Govardhan | Design | 3- Completed | 7 | 7 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | TS-106 | Build 1-5 slider skill assessment matrix and proposal input state | 2024-11-06 | 2024-11-08 | Govardhan | Coding | 3- Completed | 6 | 6 | 6 | 6 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | TS-107 | Develop Feasibility Agent prompt chain and 0-100 scoring algorithm | 2024-11-08 | 2024-11-12 | Govardhan | Coding | 3- Completed | 8 | 8 | 8 | 8 | 8 | 7 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | TS-108 | Create Feasibility Report Modal component in React with OLED styling | 2024-11-12 | 2024-11-14 | Govardhan | Coding | 3- Completed | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0
US-05 | TS-109 | Wireframe Faculty Dashboard layout, navigation bar, and review shell | 2024-11-04 | 2024-11-06 | Supriya | Design | 3- Completed | 6 | 6 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | TS-110 | Implement Faculty React view with initial student project cards and status | 2024-11-06 | 2024-11-09 | Supriya | Coding | 3- Completed | 7 | 7 | 7 | 7 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | TS-111 | Define faculty evaluation criteria and cohort health metrics schemas | 2024-11-09 | 2024-11-11 | Supriya | Analysis | 3- Completed | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-08 | TS-112 | Research LLM prompt engineering techniques for tech stack heuristics | 2024-11-12 | 2024-11-14 | Supriya | Analysis | 3- Completed | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0
US-03 | TS-113 | Set up MongoDB Atlas cloud cluster, network IP access, and URI security | 2024-11-04 | 2024-11-06 | Hemapriya | Build | 3- Completed | 6 | 6 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | TS-114 | Design MongoDB normalized schemas for Users, Projects, and Analysis Reports | 2024-11-06 | 2024-11-08 | Hemapriya | Design | 3- Completed | 7 | 7 | 7 | 7 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | TS-115 | Build initial database seeding and connection health check script | 2024-11-09 | 2024-11-11 | Hemapriya | Coding | 3- Completed | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-20 | TS-116 | Draft Sprint 1 Agile Project Charter, RACI Matrix, and DoR/DoD documents | 2024-11-12 | 2024-11-14 | Hemapriya | Documentation | 3- Completed | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 0 | 0 | 0 | 0 | 0
SPRINT 2 BACKLOG — Scope Governance, Tech Stack, Risk Matrix & Agent Chaining
US-07 | TS-201 | Build sequential agent execution pipeline in agent_service.py | 2024-11-18 | 2024-11-20 | Karthik | Coding | 3- Completed | 8 | 8 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | TS-202 | Implement LiteLLM retry backoff wrapper (litellm_patch.py) for rate limits | 2024-11-21 | 2024-11-23 | Karthik | Coding | 3- Completed | 6 | 6 | 6 | 6 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | TS-203 | Develop REST endpoints for /scope, /tech_stack, and /risk with Pydantic v2 | 2024-11-24 | 2024-11-26 | Karthik | Coding | 3- Completed | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-19 | TS-204 | Write integration tests for multi-agent sequential pipeline execution | 2024-11-27 | 2024-11-29 | Karthik | Integration Test | 3- Completed | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0 | 0 | 0 | 0
US-06 | TS-205 | Develop Scope Definition Agent (Agent 2) with In-Scope vs Out-of-Scope limits | 2024-11-18 | 2024-11-21 | Govardhan | Coding | 3- Completed | 8 | 8 | 6 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | TS-206 | Create Scope Report UI modal with categorized deliverables and MVP criteria | 2024-11-21 | 2024-11-24 | Govardhan | Coding | 3- Completed | 6 | 6 | 6 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | TS-207 | Chain Feasibility report outputs into Scope Agent input payload context | 2024-11-25 | 2024-11-27 | Govardhan | Integration Test | 3- Completed | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0
US-02 | TS-208 | Integrate responsive layout fixes and OLED theme consistency across modals | 2024-11-28 | 2024-11-30 | Govardhan | Design | 3- Completed | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0
US-08 | TS-209 | Build Tech Stack Recommender Agent (Agent 3) tailored to team skill ratings | 2024-11-18 | 2024-11-21 | Supriya | Coding | 3- Completed | 7 | 7 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-08 | TS-210 | Build TechStackReportModal.jsx in React with categorized library tags | 2024-11-21 | 2024-11-23 | Supriya | Coding | 3- Completed | 5 | 5 | 5 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-09 | TS-211 | Develop Multi-Vector Risk Assessment Agent (Agent 4) with P × I scoring | 2024-11-24 | 2024-11-27 | Supriya | Coding | 3- Completed | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0
US-09 | TS-212 | Implement interactive RiskHeatmapMatrix.jsx component in React | 2024-11-28 | 2024-11-30 | Supriya | Coding | 3- Completed | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 1 | 0 | 0 | 0
US-10 | TS-213 | Design MongoDB schemas for Feasibility, Scope, Tech Stack, and Risk models | 2024-11-18 | 2024-11-21 | Hemapriya | Design | 3- Completed | 7 | 7 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-10 | TS-214 | Implement local JSON fallback file storage sync in sync_to_mongo.py | 2024-11-22 | 2024-11-25 | Hemapriya | Coding | 3- Completed | 6 | 6 | 6 | 6 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-10 | TS-215 | Write schema normalization validation script to verify document integrity | 2024-11-26 | 2024-11-28 | Hemapriya | System Test | 3- Completed | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 1 | 0 | 0 | 0 | 0
US-20 | TS-216 | Document Sprint 2 user stories, acceptance criteria, and Defect Log entries | 2024-11-29 | 2024-12-01 | Hemapriya | Documentation | 3- Completed | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 2 | 0 | 0
SPRINT 3 BACKLOG — Tracking Agent, Student Roadmap, Replanner & AI Chat
US-11 | TS-301 | Develop Tracking & Timeline Agent (Agent 5) generating 5 execution phases | 2024-12-02 | 2024-12-05 | Karthik | Coding | 3- Completed | 8 | 8 | 6 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-11 | TS-302 | Implement task dependency graph generation and estimated phase completion | 2024-12-05 | 2024-12-08 | Karthik | Coding | 3- Completed | 7 | 7 | 7 | 7 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-11 | TS-303 | Build API endpoints /tracking/update_task and /milestones/{id} for updates | 2024-12-09 | 2024-12-11 | Karthik | Coding | 3- Completed | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 1 | 0 | 0 | 0 | 0 | 0
US-19 | TS-304 | Write automated tests for milestone status updates and task toggling | 2024-12-12 | 2024-12-14 | Karthik | Unit Test | 3- Completed | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0
US-12 | TS-305 | Implement SprintTimelineView.jsx with collapsible accordions and checkboxes | 2024-12-02 | 2024-12-05 | Govardhan | Coding | 3- Completed | 8 | 8 | 6 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-12 | TS-306 | Build real-time completion percentage progress bar with dynamic colors | 2024-12-06 | 2024-12-08 | Govardhan | Coding | 3- Completed | 5 | 5 | 5 | 5 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-14 | TS-307 | Build ChatbotPanel.jsx with chat history memory and suggested prompts | 2024-12-09 | 2024-12-12 | Govardhan | Coding | 3- Completed | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 5 | 3 | 1 | 0 | 0 | 0 | 0
US-14 | TS-308 | Integrate Web Speech API (webkitSpeechRecognition) for hands-free voice input | 2024-12-12 | 2024-12-14 | Govardhan | Coding | 3- Completed | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 1 | 0 | 0
US-13 | TS-309 | Develop delay detection algorithm comparing actual progress vs planned dates | 2024-12-02 | 2024-12-05 | Supriya | Coding | 3- Completed | 7 | 7 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-13 | TS-310 | Implement Dynamic Replanner Agent recalculating downstream phase deadlines | 2024-12-06 | 2024-12-09 | Supriya | Coding | 3- Completed | 8 | 8 | 8 | 8 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-13 | TS-311 | Create Re-Plan Roadmap trigger modal in Student view with diff summary | 2024-12-10 | 2024-12-12 | Supriya | Coding | 3- Completed | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 1 | 0 | 0 | 0 | 0
US-16 | TS-312 | Design faculty milestone approval workflow modal and notification schemas | 2024-12-12 | 2024-12-14 | Supriya | Design | 3- Completed | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 1 | 0 | 0
US-15 | TS-313 | Implement MongoDB ChatMessage schema with project ID and timestamp index | 2024-12-02 | 2024-12-05 | Hemapriya | Coding | 3- Completed | 6 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-15 | TS-314 | Optimize chat history query performance with compound indexing (<50ms) | 2024-12-06 | 2024-12-08 | Hemapriya | Build | 3- Completed | 5 | 5 | 5 | 5 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-15 | TS-315 | Build data sync verification script between React optimistic state & Mongo | 2024-12-09 | 2024-12-11 | Hemapriya | System Test | 3- Completed | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 2 | 0 | 0 | 0 | 0 | 0
US-20 | TS-316 | Author Sprint 3 Agile burndown log, standup impediment sheet, and test cases | 2024-12-12 | 2024-12-15 | Hemapriya | Documentation | 3- Completed | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 1 | 0 | 0
SPRINT 4 BACKLOG — Faculty Governance, Academic Doc Gen, E2E Testing & Release
US-18 | TS-401 | Build production multi-stage Dockerfile and configure Render deployment | 2024-12-16 | 2024-12-18 | Karthik | Build | 3- Completed | 7 | 7 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-18 | TS-402 | Configure Vercel client-side routing rewrites and API CORS security policy | 2024-12-19 | 2024-12-21 | Karthik | Build | 3- Completed | 5 | 5 | 5 | 5 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-19 | TS-403 | Execute automated regression test suite: 118 unit and integration tests | 2024-12-22 | 2024-12-25 | Karthik | System Test | 3- Completed | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0
US-19 | TS-404 | Resolve API latency bottlenecks and configure connection pooling limits | 2024-12-26 | 2024-12-28 | Karthik | Coding | 3- Completed | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0
US-19 | TS-405 | Conduct OLED Dark Theme UI polish, typography audit, and mobile responsiveness | 2024-12-16 | 2024-12-19 | Govardhan | Design | 3- Completed | 7 | 7 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-14 | TS-406 | Add suggested prompt quick-action chips and copy-to-clipboard in Chatbot | 2024-12-19 | 2024-12-21 | Govardhan | Coding | 3- Completed | 5 | 5 | 5 | 5 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-12 | TS-407 | Refactor Student Dashboard layout shell and optimize component render tree | 2024-12-22 | 2024-12-25 | Govardhan | Coding | 3- Completed | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0
US-19 | TS-408 | Cross-browser testing (Chrome, Firefox, Safari) and accessibility verification | 2024-12-26 | 2024-12-28 | Govardhan | System Test | 3- Completed | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 2 | 0 | 0 | 0
US-16 | TS-409 | Build Faculty Cohort Overview displaying student velocity and health status | 2024-12-16 | 2024-12-19 | Supriya | Coding | 3- Completed | 8 | 8 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-16 | TS-410 | Implement At-Risk flagging engine highlighting stalled or delayed student teams | 2024-12-19 | 2024-12-22 | Supriya | Coding | 3- Completed | 6 | 6 | 6 | 6 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-16 | TS-411 | Implement Faculty milestone review and official timestamped digital sign-off | 2024-12-22 | 2024-12-25 | Supriya | Coding | 3- Completed | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0
US-16 | TS-412 | Build Faculty broadcast announcement engine with cohort banner alerts | 2024-12-26 | 2024-12-28 | Supriya | Coding | 3- Completed | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0
US-17 | TS-413 | Implement Academic Document Generator Agent (Agent 7) in doc_generator_agent.py | 2024-12-16 | 2024-12-19 | Hemapriya | Coding | 3- Completed | 8 | 8 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-17 | TS-414 | Build Project Synopsis and Methodology drafting templates with PDF export | 2024-12-19 | 2024-12-22 | Hemapriya | Coding | 3- Completed | 6 | 6 | 6 | 6 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-20 | TS-415 | Compile Requirements Traceability Matrix (RTM) linking 20 US to tests and code | 2024-12-23 | 2024-12-25 | Hemapriya | Documentation | 3- Completed | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 1 | 0 | 0 | 0 | 0 | 0
US-20 | TS-416 | Finalize Defect Tracker, Unit Test Plan, and Capstone Presentation artifacts | 2024-12-26 | 2024-12-28 | Hemapriya | Documentation | 3- Completed | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0 | 0 | 0

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | [Karthik] JWT signature algorithm security configuration & secret key rotation | Configured secure HS256 algorithm with .env environment variable secret loading.
Sprint 1 | Day 4 | [Govardhan] Multi-step onboarding form state loss on accidental page refresh | Integrated localStorage persistent draft saving in React with automatic form restore.
Sprint 1 | Day 6 | [Hemapriya] MongoDB Atlas connection timeout during local corporate firewall/IP whitelist | Configured network security IP access and built graceful JSON file store fallback.
Sprint 1 | Day 8 | [Supriya] Unclear pedagogical metrics for evaluating student project progress | Consulted faculty guidelines; established 5 core dimensions for cohort health analytics.
Sprint 1 | Day 11 | [Govardhan & Karthik] Feasibility Agent LLM output occasionally returning non-JSON text | Enforced Pydantic schema validation and integrated json-repair parsing heuristics.
Sprint 2 | Day 3 | [Karthik] Groq API rate limits (TPM/RPM) hit when testing multiple agent pipelines | Implemented litellm_patch.py with exponential backoff retry and sequential chaining.
Sprint 2 | Day 5 | [Govardhan] Scope Agent prompt occasionally omitting explicit Out-of-Scope boundaries | Refined system prompt with strict negative boundary enforcement and 3+ MVP deliverables.
Sprint 2 | Day 7 | [Supriya] Tech stack recommendations proposing libraries mismatched to beginner skills | Integrated skill-weighted filtering logic in tech_stack_agent.py to prioritize student ratings.
Sprint 2 | Day 10 | [Supriya] 5x5 Risk Heatmap grid alignment breaking on smaller laptop viewports | Rebuilt RiskHeatmapMatrix.jsx using responsive CSS Grid with dynamic SVG cell overlays.
Sprint 2 | Day 12 | [Hemapriya] MongoDB schema foreign key inconsistencies between projects and reports | Created scripts/normalize_database.py to migrate legacy documents and enforce schema refs.
Sprint 3 | Day 2 | [Karthik] Milestone agent generating non-sequential timeline dates for complex scopes | Added topological sort dependency validator in tracking_agent.py to enforce phase logic.
Sprint 3 | Day 5 | [Govardhan] React state lag when toggling task check-offs rapidly on high latency | Implemented optimistic UI state updates with debounced background MongoDB sync.
Sprint 3 | Day 7 | [Supriya] Dynamic replanner recalculating completed milestones instead of future phases | Added phase status lock so only IN_PROGRESS and UPCOMING phases undergo date shifts.
Sprint 3 | Day 9 | [Govardhan] Web Speech API microphone permission denied when tested on local HTTP URL | Configured Vite HTTPS development certificate and implemented fallback keyboard text input.
Sprint 3 | Day 12 | [Hemapriya] Chatbot message retrieval latency exceeding 150ms as message count grew | Created compound index on (project_id, timestamp) in MongoDB, reducing latency to <35ms.
Sprint 4 | Day 2 | [Supriya] Faculty dashboard cohort table re-rendering sluggishly with 25+ student teams | Implemented React memoization (useMemo, React.memo) and virtualized table rows.
Sprint 4 | Day 4 | [Hemapriya] Document Generator formatting breaking markdown tables on synopsis export | Integrated structured Markdown table generator with pre-validated university template blocks.
Sprint 4 | Day 6 | [Karthik] Docker build failing on Render due to missing frontend static build assets | Converted Dockerfile to multi-stage build: Node 20 builder stage copying dist/ into FastAPI.
Sprint 4 | Day 8 | [Govardhan & Supriya] Broadcast notification banner overlapping top navbar on mobile | Adjusted z-index stack and layout flex containers for persistent top-level banner alert.
Sprint 4 | Day 10 | [Team] Full system regression test execution and final Capstone Viva dress rehearsal | Ran test_all_agents.py (118/118 tests passed green); validated live presentation slides.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2024-11-04 | 2024-11-17 | Karthik | Writing Pydantic schemas before endpoint logic | Assuming API payload formats without contracts | Collaborating on FastAPI test harnesses | Enforced strict Pydantic v2 validation across all backend auth endpoints.
2 | Sprint 1 | 2024-11-04 | 2024-11-17 | Govardhan | Prototyping responsive layouts on mobile early | Postponing error state handling until end | Creating reusable OLED Dark UI components | Built centralized toast notification system and robust error boundary.
3 | Sprint 1 | 2024-11-04 | 2024-11-17 | Supriya | Consulting faculty rubric before feature build | Hardcoding mock student evaluation criteria | Designing intuitive navigation dashboards | Mapped student progress metrics directly to faculty evaluation rubric.
4 | Sprint 1 | 2024-11-04 | 2024-11-17 | Hemapriya | Documenting collection schemas in markdown | Relying solely on remote Atlas connections | Verifying database indexes during creation | Implemented local JSON fallback cache to prevent local development halts.
5 | Sprint 2 | 2024-11-18 | 2024-12-01 | Karthik | Adding exponential retry backoff on API calls | Sending concurrent burst queries to Groq LLM | Maintaining comprehensive pytest coverage | Developed litellm_patch.py retry wrapper with token usage tracking.
6 | Sprint 2 | 2024-11-18 | 2024-12-01 | Govardhan | Inspecting raw LLM outputs with edge cases | Using single large prompt for multi-tasks | Chaining modular agents sequentially | Split monolithic prompts into chained Feasibility-to-Scope agent pipelines.
7 | Sprint 2 | 2024-11-18 | 2024-12-01 | Supriya | Testing visual components with extreme values | Overcomplicating risk calculations | Creating interactive color-coded heatmaps | Fine-tuned 5x5 matrix thresholds to clearly flag high-risk technical items.
8 | Sprint 2 | 2024-11-18 | 2024-12-01 | Hemapriya | Running database normalization tests daily | Allowing unindexed collection queries | Maintaining automated seed data scripts | Created normalize_database.py ensuring all foreign keys link accurately.
9 | Sprint 3 | 2024-12-02 | 2024-12-15 | Karthik | Using topological sorting for timeline tasks | Assuming linear chronological dependencies | Writing unit tests for timeline edge cases | Engineered dependency resolver ensuring no milestone starts before predecessors.
10 | Sprint 3 | 2024-12-02 | 2024-12-15 | Govardhan | Implementing optimistic UI state in React | Waiting for slow network roundtrips on toggle | Integrating native browser APIs like Speech | Implemented instantaneous checkbox response with debounced background sync.
11 | Sprint 3 | 2024-12-02 | 2024-12-15 | Supriya | Locking completed milestones during replanning | Shifting entire timeline when one task slips | Simulating edge-case delay scenarios | Enhanced dynamic replanner to reschedule only future active phases.
12 | Sprint 3 | 2024-12-02 | 2024-12-15 | Hemapriya | Benchmarking query response times under load | Storing uncompressed chat payload objects | Maintaining Agile burndown tracking updates | Added compound index on (project_id, timestamp) cutting latency by 75%.
13 | Sprint 4 | 2024-12-16 | 2024-12-29 | Karthik | Multi-stage Docker builds to optimize image size | Manual cloud configuration on hosting sites | Automated CI/CD regression verification | Dockerized fullstack app reducing deployment image footprint to under 250MB.
14 | Sprint 4 | 2024-12-16 | 2024-12-29 | Govardhan | Pre-Viva end-to-end user walkthroughs | Overlooking cross-browser speech quirks | Polishing OLED aesthetic micro-interactions | Tested live speech engine across Chrome/Edge with graceful keyboard fallback.
15 | Sprint 4 | 2024-12-16 | 2024-12-29 | Supriya | Memoizing heavy data tables in React views | Re-rendering entire dashboard on filter change | Adding live broadcast alert notifications | Optimized Faculty Dashboard render cycle ensuring 60fps smooth scrolling.
16 | Sprint 4 | 2024-12-16 | 2024-12-29 | Hemapriya | Exporting documents in both Markdown & PDF | Postponing RTM validation to after coding | Documenting test evidence for Viva defense | Generated comprehensive RTM linking all 20 User Stories to passing tests.