## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Govardhan | 2024-11-06 | JWT token expiration time defaulted to 15 mins causing premature logout during long onboarding forms | Sprint 1 | Karthik | Logical | Extended access token expiration to 8 hours and implemented silent refresh handling | 2024-11-07 | Closed | Verified session continuity during full submission workflow
2 | Karthik | 2024-11-08 | Skill assessment rating sliders allowed negative values or NaN when typed manually | Sprint 1 | Govardhan | User Interface | Enforced min=1 max=5 constraints in React input handlers with auto-clamping | 2024-11-09 | Closed | Validated slider range and input sanitization
3 | Supriya | 2024-11-10 | MongoDB Atlas IP whitelist prevented backend connection on dynamic local IP changes | Sprint 1 | Hemapriya | Standards | Configured secure 0.0.0.0/0 IP whitelist with strong credential auth and fallback JSON store | 2024-11-11 | Closed | Offline and dynamic IP access verified seamlessly
4 | Govardhan | 2024-11-20 | Groq API rate limits (HTTP 429) thrown during rapid multi-agent sequential pipeline execution | Sprint 2 | Karthik | Logical | Integrated litellm_patch.py with 3-tier exponential backoff and fallback model selection | 2024-11-21 | Closed | 10 sequential test iterations executed with zero unhandled rate limits
5 | Hemapriya | 2024-11-22 | Scope Agent occasionally generated markdown headers inside JSON string properties | Sprint 2 | Govardhan | Standards | Updated system prompt instructions and added regex markdown stripper to output parser | 2024-11-23 | Closed | Pydantic ScopeReport schema strictly validates all outputs
6 | Karthik | 2024-11-25 | Tech Stack Recommender suggested advanced Kubernetes/Docker for a beginner student with level 1 DevOps | Sprint 2 | Supriya | Logical | Added skill-rating threshold filter in tech_stack_agent.py to suggest simpler alternatives | 2024-11-26 | Closed | Verified tailored recommendations match beginner student skills
7 | Hemapriya | 2024-11-28 | Risk heatmap 5x5 grid cells misaligned when viewed on mobile screens under 480px | Sprint 2 | Supriya | User Interface | Added responsive horizontal scroll wrapper and scalable CSS grid dimensions | 2024-11-29 | Closed | Tested on iPhone 14 and Pixel 7 mobile viewport simulations
8 | Govardhan | 2024-12-04 | Timeline generator agent created overlapping dates between Phase 1 and Phase 3 | Sprint 3 | Karthik | Logical | Implemented topological milestone scheduling algorithm with strict predecessor dates | 2024-12-05 | Closed | Validated all 5 milestone phases maintain chronological sequence
9 | Supriya | 2024-12-07 | Task checkbox toggle caused 1.2s noticeable UI delay waiting for MongoDB network roundtrip | Sprint 3 | Govardhan | Maintainability | Implemented optimistic state update in React with debounced background database sync | 2024-12-08 | Closed | Instant UI feedback achieved (<16ms 60fps)
10 | Karthik | 2024-12-10 | Web Speech API threw NotAllowedError when accessing microphone on unencrypted localhost | Sprint 3 | Govardhan | User Interface | Added graceful browser permission error handler toast and fallback keyboard text mode | 2024-12-11 | Closed | Graceful toast warning prompts user if microphone is blocked
11 | Govardhan | 2024-12-18 | Faculty Dashboard cohort table re-rendered all 25 rows on single milestone sign-off toggle | Sprint 4 | Supriya | Maintainability | Memoized student row components with React.memo and optimized state updater callback | 2024-12-19 | Closed | Only affected student row re-renders on sign-off update
12 | Karthik | 2024-12-21 | Academic document synopsis export truncated long project descriptions containing double quotes | Sprint 4 | Hemapriya | Logical | Sanitized JSON character escapes and normalized markdown template string interpolation | 2024-12-22 | Closed | Generated complete 4-page academic synopsis document with zero truncation

## Sheet2
Logical
User Interface
Maintainability
Standards
Others